Taking forward Talent Match

Deadline for submission of the first prospectus is 5th November 2012

In preparation the following issues will need to be resolved:

- Identification of a lead partner

- Identification and gathering of supporting evidence and data

- Building a delivery partnership

- Mapping existing provision

- Embedding voice of young people from the outset – identification of current market success and failure

- Identifying potential sources of match funding to increase programme impact

In order to achieve this it is proposed that the following timetable be followed:

| Meeting | Purpose | Attendees | Date / timescale |
| --- | --- | --- | --- |
| Steering group meeting | Develop plans for addressing each of the points 1-6 above | Selected key stakeholders from across 3 sectors | 2nd week Sept |
| Working groups | Progress development plans to address points 2-6 above | Steering group member leads plus wider partnership input. Secretariat by One EM. Work may be completed electronically | September to early Oct |
| Partnership event | Present progress and outline approaches to the wider partnership for shaping and input | All registered interested parties | w/c 8th Oct |
| Working groups | Amend deliver proposals following partnership input. Development of outline prospectus content | Steering group member leads plus wider partnership input. Secretariat by One EM with lead partner coordination. Work may be completed electronically | October |
| Steering group meeting | Review progress and finalise prospectus | Steering group | w/c 29 Oct |
| Submission | Submit outline prospectus setting out vision for change and target areas | Lead Partner | 5th Nov 12 noon |

Process:

One EM have been gathering contact details of interested parties over the summer.  A questionnaire will be circulated to identify what role these interested parties wish to play w/c 20th Aug.

The initial scoping (Steering Group) meeting will be held early Sept with a limited number of invitees.  Steering group members must be able to demonstrate at least one of the following:

- A strategic role in shaping services for the benefit of the target group;

- access to a wider cross sector partnership to support the work of the partnership;

- ability to engage and involve young people in the target audience in the process;

- access to data or evidence that will help identify need and/or existing provision;

- the views and perspectives of employers;

The first meeting of the steering group will be tasked with:

- identifying sources of evidence and mechanisms for mapping provision – including gaps in knowledge which will need to be filled;

- ideas and approaches to engaging young people especially around developing solutions which work and address current market failure;

- approaches to engaging employers;

- considering potential sources of match;

- agreeing a process for appointing a lead partner

Each of these will then be assigned to lead from amongst the steering group to take forward with support from the secretariat.

Initial members of the steering group are suggested as:

| Organisation | Role | Contact |
| --- | --- | --- |
| Nottinghamshire ESB | Employment and Skills Board | David Kirkham |
| Derby City ESB | Employment and Skills Board |  |
| Derbyshire ESB | Employment and Skills Board |  |
| Job Centre Plus (Derbys) | Data and evidence, service mapping | Sue Fielding |
| Job Centre Plus (Notts) | Data and evidence, service mapping | Andy Pidlznyj |
| Business in the Community | Private sector engagement | Heidi Watson |
| Derbys & Notts Chamber of Commerce | Employer engagement | George Cowcher |
| Federation of Small Businesses | Employer engagement |  |
| Enable | VCS Learning and Skills consortium (Notts) | Don Hayes |
| DLDC | VCS Learning and Skills consortium (Derbys) | Lisa Vernon |
| 3 x youth organisations focussed on target audience | Broxtowe Youth Homeless |  |
| One EM | Secretariat | Rachel Quinn |
| Big Lottery | Advisor | Mick McGrath |